## Overall Estimation
Setup user info database/table | 2hr-4hr
Log in display/input | 50min-2hr
Send user to google if they have a google account | 45min-2hr
Pull user data/email from google database | 1hr-2hr
Display create account info | 2hr-3hr
Send user an email to authenticate account | 30min
Authenticate user once they click on email link | 45min-1hr
Create display for them to input home address/calendar events | 50min-2hr
Save user home address/calendar to database | 1hr-2hr
Save user login info/log email and password to database | 1hr-2hr
Create logout display | 50min-2hr
Logging out user | 30min
Total Time | 12hr-23hr

## Haoran's estimation
Create a login link that links to gmail | 1 hour
create a registration process for those who don't have a gmail account | 4 hours
obtain personal data from gamil account | 2 hours
creating front-end website display of the login page | 4 hours
automatically send confirmation email | 1 hour
create a data base to save all users' login information | 2 hours

## Ivan's Estimation
Login/Logout User Story
| Setup user info database/table | 3hr-4hr
| Log in display/input | 50min-2hr
Google Account | Send user to google if they have a google account | 45min
| Pull user data/email from google database | 1hr-2hr
| Display create account info | 50min-2hr
| Send user an email to authenticate account | 30min
No Google Account | Authenticate user once they click on email link | 45min-1hr
| Create display for them to input home address/calendar events | 50min-2hr
| Save user home address/calendar to database | 1hr-2hr
| Save user login info/log email and password to database | 1hr-2hr
| Create logout display | 50min-2hr
| Logging out user | 30min

## Josh's Estimation
Setup user info database/table | 2 hrs
Log in display/input | 2 hrs
Send user to google if they have a google account | 2 hrs
Pull user data/email from google database | 1 hr
Display create account info | 1 hr
Send user an email to authenticate account | 30 min
Authenticate user once they click on email link | 30 min
Create display for them to input home address/calendar events | 1 hr
Save user home address/calendar to database | 1 hr
Save user login info/log email and password to database | 1 hr
Create logout display | 1 hr
Logging out user | 30 min